## Q2 2026 – Samara
Samara Tager · Q2 2026 AI Co-Pilot Timeline · April – June
|  | APRIL |  |  |  | MAY |  |  |  | JUNE
PHASE | ACTIVITY | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | NOTES / ASSUMPTION
|  | Apr 1 | Apr 7 | Apr 14 | Apr 21 | Apr 28 | May 5 | May 12 | May 19 | May 26 | Jun 2 | Jun 9 | Jun 16 | Jun 23
🏖 TIME OFF |  | Apr 14: 1–2 days move prep; May 5: Moving 🏠 | April: 1–2 days wk of Apr 14 · May: several days for move wk of May 5
PHASE 1 · VISION SPRINT
Vision Sprint prep | bar: Apr 1 to Apr 14
| ★ Vision Workshop · Apr 10 | [13 empty] | HMW ideation → 2–3 co-pilot concepts → qual + A/B test plan | bar: Apr 7 to Apr 14
| Workshop synthesis + quarter plan | [13 empty] | Refine concepts, define qual test design, confirm Q2 sequence | bar: Apr 7 to Apr 14
PHASE 2 · CONCEPT DEVELOPMENT & PROTOTYPING
Concept sketch refinement — 2–3 directions | bar: Apr 14 to Apr 21
| Prototype build | [13 empty] | ~40% of quarter allocated to learning new AI / vibe coding tools | bar: Apr 14 to May 5
PHASE 3 · QUAL + EARLY A/B
Recruit qual participants
Early A/B test | bar: May 5 to May 19
Qual sessions | bar: May 5 to May 12
Qual synthesis | bar: May 19
PHASE 4 · HYPOTHESIS DEFINITION
Define hypotheses + prioritize A/B test sequence | bar: May 26
PHASE 5 · A/B TESTING
Hypothesis 1 · TBD from workshop | bar: Jun 2
Hypothesis 2 · TBD from workshop | bar: Jun 9
Hypothesis 3 · TBD from workshop | bar: Jun 16
Hypothesis 4 · TBD from workshop | bar: Jun 23
EOQ synthesis + design | bar: Jun 23
MILESTONES
Vision Workshop | bar: Apr 7
Qual sessions begin | bar: May 12
Qual synthesis complete | bar: May 12
Hypotheses locked | bar: May 26
H1 design | bar: Jun 2
H2 design | bar: Jun 9
H3 design | bar: Jun 16
H4 design | bar: Jun 23
EOQ synthesis + design | bar: Jun 23
LEGEND
| Vision Sprint | Apr 14: Qual Research; May 5: Hypothesis Definition; May 26: A/B Testing; Jun 16: ◆ Milestone